## Dashboard
PURCHASE ORDER DASHBOARD
Live summary of purchasing activity • Sample data included.
TOTAL PURCHASE ORDERS |  | TOTAL PO VALUE (SAR) | OVERDUE ORDERS | COMPLETION RATE
8 |  | 44440 | 4 | 12.5%
ORDER STATUS SUMMARY |  |  | DELIVERY & QUANTITY METRICS
Status | Count | Share | Total ordered quantity |  | 694
Scheduled | 2 | 25% | Total received quantity |  | 295
Partially Received | 1 | 12.5% | Total outstanding quantity |  | 399
Overdue | 1 | 12.5% | Received value (approx.) |  | 18125
Overdue - Partial | 3 | 37.5%
Complete | 1 | 12.5%
Incomplete | 0 | 0%
Over-received | 0 | 0%
Follow-up tip: Filter Purchase Orders by Status to prioritize overdue orders and supplier calls.

## Purchase Orders
PURCHASE ORDER TRACKER
Enter details in blue cells. Gray cells are calculated automatically.
PO Number | Supplier ID | Supplier Name | Item / Description | Category | Order Date | Promised Delivery Date | Ordered Qty | Unit Price (SAR) | PO Value (SAR) | Received Qty | Remaining Qty | Latest Receipt Date | Status | Days Late | Notes
PO-2026-001 | SUP-001 | Northstar Industrial Supplies | Industrial fasteners | Industrial supplies | 2026-09-20 | 2026-10-05 | 100 | 125 | 12500 | 100 | 0 | 2026-10-08 | Complete |  | Sample: fully received
PO-2026-002 | SUP-003 | Eastern Packaging Co. | Packaging cartons | Packaging | 2026-09-22 | 2026-10-07 | 80 | 45 | 3600 | 25 | 55 | 2026-10-05 | Overdue - Partial | 8 | Sample: overdue partial receipt
PO-2026-003 | SUP-002 | Gulf Office Solutions | Office paper boxes | Office supplies | 2026-10-01 | 2026-10-25 | 200 | 18 | 3600 | 100 | 100 | 2026-10-10 | Partially Received | 0 | Sample: partial receipt, not yet due
PO-2026-004 | SUP-004 | BlueLine Safety Equipment | Safety gloves | Safety equipment | 2026-10-03 | 2026-10-12 | 150 | 32 | 4800 | 50 | 100 | 2026-10-12 | Overdue - Partial | 3 | Sample: overdue partial receipt
PO-2026-005 | SUP-005 | Desert Tech Components | Network adapters | IT components | 2026-10-12 | 2026-10-28 | 30 | 210 | 6300 | 0 | 30 |  | Scheduled | 0 | Sample: scheduled
PO-2026-006 | SUP-001 | Northstar Industrial Supplies | Protective eyewear | Safety equipment | 2026-10-04 | 2026-10-14 | 60 | 55 | 3300 | 20 | 40 | 2026-10-13 | Overdue - Partial | 1 | Sample: partial receipt
PO-2026-007 | SUP-002 | Gulf Office Solutions | Printer toner | Office supplies | 2026-10-13 | 2026-10-20 | 24 | 285 | 6840 | 0 | 24 |  | Scheduled | 0 | Sample: scheduled
PO-2026-008 | SUP-003 | Eastern Packaging Co. | Stretch film rolls | Packaging | 2026-10-01 | 2026-10-09 | 50 | 70 | 3500 | 0 | 50 |  | Overdue | 6 | Sample: overdue with no receipt
Formulas:
Latest Receipt Date = IFERROR(LOOKUP(2,1/(Receipts!$B5:B510=[PO Number]),Receipts!$C5:C510),"")
Status = IF([PO Number]="","",IF(OR([Ordered Qty]="",[Promised Delivery Date]=""),"Incomplete",IF([Received Qty]>[Ordered Qty],"Over-received",IF([Remaining Qty]=0,"Complete",IF([Received Qty]>0,IF([Promised Delivery Date]<TODAY(),"Overdue - Partial","Partially Received"),IF([Promised Delivery Date]<TODAY(),"Overdue","Scheduled"))))))
Days Late = IF(OR([PO Number]="",[Remaining Qty]=0,[Promised Delivery Date]=""),"",MAX(0,TODAY()-[Promised Delivery Date]))

## Receipts
GOODS RECEIPT LOG
Record every delivery separately. Use one row per receipt event.
Receipt ID | PO Number | Receipt Date | Quantity Received | Received By | Notes
GR-0001 | PO-2026-001 | 2026-10-02 | 40 | A. Buyer | First delivery
GR-0002 | PO-2026-001 | 2026-10-08 | 60 | A. Buyer | Balance received
GR-0003 | PO-2026-002 | 2026-10-05 | 25 | A. Buyer | Partial delivery
GR-0004 | PO-2026-003 | 2026-10-10 | 100 | A. Buyer | First delivery
GR-0005 | PO-2026-004 | 2026-10-12 | 50 | A. Buyer | Partial delivery
GR-0006 | PO-2026-006 | 2026-10-13 | 20 | A. Buyer | Partial delivery

## Suppliers
SUPPLIER DIRECTORY
Maintain supplier details here. Supplier IDs must be unique.
Supplier ID | Supplier Name | Contact Name | Phone | Email | Supply Category | Typical Lead Time (Days) | Supplier Rating (1-5)
SUP-001 | Northstar Industrial Supplies | M. Hassan | +966 5X XXX XXXX | orders@northstar.example | Industrial supplies | 7 | 4
SUP-002 | Gulf Office Solutions | A. Salem | +966 5X XXX XXXX | sales@gulfoffice.example | Office supplies | 4 | 5
SUP-003 | Eastern Packaging Co. | R. Khalid | +966 5X XXX XXXX | sales@easternpack.example | Packaging | 10 | 3
SUP-004 | BlueLine Safety Equipment | S. Omar | +966 5X XXX XXXX | procurement@blueline.example | Safety equipment | 5 | 4
SUP-005 | Desert Tech Components | N. Ali | +966 5X XXX XXXX | orders@deserttech.example | IT components | 14 | 3

## Read Me
USER GUIDE
Quick-start instructions and assumptions.
1. Start here | Review sample data, then replace it with your own. Blue cells are for manual input; gray cells contain formulas.
2. Supplier setup | Add suppliers in Suppliers. Supplier IDs must be unique. Select the matching Supplier ID in Purchase Orders.
3. Create a PO | Enter a unique PO Number, Supplier ID, item, category, order date, promised date, ordered quantity, and unit price.
4. Record deliveries | Each delivery gets its own row in Receipts. Use the exact PO Number and enter receipt date and quantity.
5. Status logic | Incomplete = required quantity or promised date is missing. Over-received = receipts exceed ordered quantity. Complete = all ordered quantity received without over-receipt. Partial statuses depend on whether the promised date has passed. No receipt after the promised date = Overdue; otherwise Scheduled.
6. Remaining quantity | Remaining Qty = MAX(Ordered Qty - Total Qty Received, 0). Over-receipts are flagged for review.
7. Dashboard | The dashboard updates when Excel recalculates. Completion Rate = complete orders divided by all entered PO Numbers.
8. Date behavior | Overdue status uses TODAY(), so it changes as the date changes. Excel recalculates formulas when opened.
9. Compatibility | Supplier Name uses INDEX/MATCH for broader Excel compatibility. Formula separators can vary by regional settings.
10. Limitations | This is an Excel tracker, not an ERP. It does not send emails, approve purchases, or enforce company policy.
11. Currency | Amounts are displayed in SAR. Change number formats if needed.
12. Test before use | Test complete, partial, overdue, no-receipt, and over-receipt scenarios before using live data. Keep a backup.